## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	ssad24
PROJECT NAME	Mobile Video Invitation by YourEvent.co
PROJECT MENTOR	Mr Sri Harsha and Mr Abhilash Inumella
TEAM MEMBERS	Jalpreet Singh Nanda
	Raj Patel
	Manas Tewari
	Vikram Ahuja

## Team_Status
TEAM NAME	ssad24
PROJECT NAME	Mobile Video Invitation by YourEvent.co
PROJECT MENTOR	Mr Sri Harsha and Mr Abhilash Inumella

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn Eclipse	Preparation	Jalpreet, Raj, Manas, Vikram	2	3	Done	Using IDEs can make our job easier	-1	33.3333333333
Role preferences	Coordination	Jalpreet, Raj, Manas, Vikram	0.5	0.3	Done		0.2	66.6666666667
Learn Android	Preparation	Jalpreet, Raj, Manas, Vikram	10	9	Done	It is the core of our project	1	11.1111111111
UI Inspirations	Design	Raj, Vikram	6	6	Done	This will help us in designing our app.	0	0
Flow of the App	Design	Raj, Manas, Jalpreet	2	1	Done
Project Plan writeup	Documentation	Raj, Manas	1	2	Done		-1	50
UI Designers	Design	Jalpreet, Manas	10	10	Done	We are designing the prototype of the app.	0	0
Research existing technology	Preparation	Jalpreet, Raj, Manas, Vikram	4	4	Done		0	0
Project synopsis writeup	Documentation	Jalpreet	1	0.7	Done		0.3	42.8571428571
Identify role owners	Preparation	Sri Harsha(Client)	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	Jalpreet, Raj, Manas, Vikram	3	3	Done		0	0
Status tracker	Documentation	Jalpreet, Raj	1	1	Done		0	0
Week 7 (sept 12 - sept 18)
SRS document	Documentation	Jalpreet, Manas, Raj	2	3	Done	Requirements documentation	-1	33.3333333333
Screen Finalization(Photoshop)	Design	Jalpreet, Manas	8	8	Done	Making expected screens in Photoshop	0	0
Status tracker	Documentation	Raj, Jalpreet	0.5	0.5	Done		0	0
Workflow Modifications(Proto.io)	Design	Raj, Vikram	2	2	Done	Workflow of screens decided before finalizing screens in photoshop	0	0
Start implentation	Development	TBD			Delayed
Learn Android	Preparation	Raj, Jalpreet, Manas, Vikram	8	8	Done		0	0
Week 8 (sept 19 - sept 25)
Status tracker	Documentation	Raj, Jalpreet	0.5	0.25	Done		0.25	100
UI modifications(Photoshop)	Design	Jalpreet, Manas	2	2	Done		0	0
Reading apps on parse	Preparation	Raj, Jalpreet, Manas, Vikram	8	10	Done	Getting familiar with parse API by presenting apps to client
Presenting these apps	Preparation	Raj, Jalpreet, Manas, Vikram	1	0.5	Done
Test plan document	Documentation	Raj, Jalpreet	1	1	Done
Team Meeting	Coordination	Raj, Jalpreet, Manas, Vikram	2	2	Done		0	0
Week 9 (sept 26 - oct 3)
Start implentation	Development	Raj, Jalpreet, Manas, Vikram	6		Planned
Team Meeting	Coordination	Raj, Jalpreet, Manas, Vikram	2		Planned
Make first screen of the app	Development	Raj, Jalpreet, Manas, Vikram	4		Planned	Make action bar of select event screen
Completing Flow in invision	Design	Jalpreet	1		Ongoing
Status tracker	Documentation	Raj, Jalpreet	0.5		Ongoing
Week 10

Week 11

Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	ssad24
PROJECT NAME	Mobile Video Invitation by YourEvent.co
PROJECT MENTOR	Mr Sri Harsha and Mr Abhilash Inumella

Actvities	Jalpreet Singh Nanda		Raj Patel		Manas Tewari		Vikram Ahuja		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
Learn Eclipse	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5	Err:509	Err:509
Role preferences	0.16	0.16	0.16	0.16	0.16	0.16	0.16	0.16	Err:509	Err:509
Learn Android	2.5	2	2.5	2	2	2	2.5	2	Err:509	Err:509
UI Inspirations			3	2			3	1	Err:509	Err:509
Project Plan writeup			1	0.5	1	0.5			Err:509	Err:509
UI Designers	6	5			6	4			Err:509	Err:509
Research existing technology	1	1	1	1	1	1	1	1	Err:509	Err:509
Project synopsis writeup	1	0.7					Err:509	Err:509
Identify role owners						Err:509	Err:509
Team Meeting	3	3	3	3	3	3	3	3	Err:509	Err:509
Status tracker	0.5	0.5	0.5	0.5					Err:509	Err:509
Week 7 (sept 12 - sept 18)
SRS document	1	1	0	0.5	1	1.5			Err:509	Err:509
Screen Finalization(Photoshop)	5	4			5	4			Err:509	Err:509
Status tracker	0.25	0.2	0.25	0.2					Err:509	Err:509
Workflow Modifications(Proto.io)			3	3			3	3	Err:509	Err:509
Start implentation						Err:509	Err:509
Learn Android	2	1	2	1	2	1	2	1	Err:509	Err:509
Week 8 (sept 19 - sept 25)
Status tracker	0.5	0.25	0.5	0.25					Err:509	Err:509
UI modifications(Photoshop)	2	2			2	1			Err:509	Err:509
Team meeting	2	2	2	2	2	2	2	2
Reading apps on parse	2	2	2	2	2	2	2	2
Presenting these apps	0.5	0.2	0.5	0.2	0.5	0.2	0.5	0.2
Test plan document	1	1	1	1					Err:509	Err:509
Week 9 (sept 26 - oct 3)
Start implentation	1.5		1.5		1.5		1.5		Err:509	Err:509
Make first screen of the app	1		1		1		1		Err:509	Err:509
Team Meeting	2		2		2		2
Completing Flow in invision	1
Status tracker	0.5		0.5
Week 10						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 11						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 12						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 13						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 14						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 15						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 16						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
Week 17						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
0						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509
						Err:509	Err:509