## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	ssad24
PROJECT NAME	Mobile Video Invitation by YourEvent.co
PROJECT MENTOR	Mr Sri Harsha and Mr Abhilash Inumella
TEAM MEMBERS	Jalpreet Singh Nanda
	Raj Patel
	Manas Tewari
	Vikram Ahuja

## Team_Status
TEAM NAME	ssad24
PROJECT NAME	Mobile Video Invitation by YourEvent.co
PROJECT MENTOR	Mr Sri Harsha and Mr Abhilash Inumella

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn Eclipse	Preparation	Jalpreet, Raj, Manas, Vikram	2	3	Done	Using IDEs can make our job easier	-1	33.3333333333
Role preferences	Coordination	Jalpreet, Raj, Manas, Vikram	0.5	0.3	Done		0.2	66.6666666667
Learn Android	Preparation	Jalpreet, Raj, Manas, Vikram	17		Ongoing	It is the core of our project
UI Inspirations	Design	Raj, Vikram	6		Planned	This will help us in designing our app.
Flow of the App	Design	Raj, Manas, Jalpreet	2	1	Done
Project Plan writeup	Documentation	Raj, Manas	1	2	Done		-1	50
UI Designers	Design	Jalpreet, Manas	12		Planned	We are designing the prototype of the app.
Research existing technology	Preparation	Jalpreet, Raj, Manas, Vikram	4	4	Done		0	0
Project synopsis writeup	Documentation	Jalpreet	1	0.7	Done		0.3	42.8571428571
Identify role owners	Preparation	Sri Harsha(Client)	1	0.6	Done	Multiple roles are OK - think about role & reponsibility distribution	0.4	66.6666666667
Team Meeting	Coordination	Jalpreet, Raj, Manas, Vikram	3		Planned
Status tracker	Documentation	Jalpreet, Raj	1	1	Done		0	0
Week 7 (sept 12 - sept 18)

Week 8 (sept 19 - sept 25)

Week 9

Week 10

Week 11

Week 12

Week 13

Week 14

Week 15

Week 16

Week 17

## Individual_Status
TEAM NAME	ssad24
PROJECT NAME	Mobile Video Invitation by YourEvent.co
PROJECT MENTOR	Mr Sri Harsha and Mr Abhilash Inumella

Actvities	Jalpreet Singh Nanda		Raj Patel		Manas Tewari		Vikram Ahuja				Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
Learn Eclipse	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5			2	2
Role preferences	0.16	0.16	0.16	0.16	0.16	0.16	0.16	0.16			0.64	0.64
Learn Android	4		5		4		4				17	0
UI Inspirations			3				3				6	0
Project Plan writeup			1	0.5	1	0.5					2	1
UI Designers	6				6					12	0
Research existing technology	1	1	1	1	1	1	1	1			4	4
Project synopsis writeup	1	0.7					1	0.7
Identify role owners						0	0
Team Meeting	3		3		3		3				12	0
Status tracker	0.5	0.5	0.5	0.5					1	1
Week 7 (sept 12 - sept 18)
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 8 (sept 19 - sept 25)
0						0	0
0						0	0
0						0	0
Week 9						0	0
0						0	0
0						0	0
Week 10						0	0
0						0	0
0						0	0
0						0	0
Week 11						0	0
0						0	0
0						0	0
0						0	0
Week 12						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 13						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 14						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 15						0	0
0						0	0
0						0	0
0						0	0
Week 16						0	0
0						0	0
0						0	0
0						0	0
0						0	0
Week 17						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0